## Slide 1: WP3 – Study modules Work Steps
Knowledge Triangle: Innovation, Reinforcing of Education-Research, E-Health & Medical Links
609506-EPP-1-2019.1-SE-EPPKA2-CBHE-JP
I .C. U Triangle
e-Health

## Slide 2
Role | Partner Institution | Acronym | Country | Contact person
Leader | University of Genoa | UNIGE | Italy | Dr Guido Amoretti
Co-Leader | Linnaeus University | LNU | Sweden | Dr Mosad Zineldin
Co-Leader | British University in Egypt | BUE | Egypt | Dr Samy El Ghoneimy
Co-Leader | Tallin University of Technology | TalTech | Estonia | Madli Krispin
Co-Leader | Notre Dame University | NDU | Lebanon | Dr Antoine Farhat
Co-Leader | Assiut University | ASU | Egypt | Dr Taysir H. Soliman
Co-Leader | University of Sinai | SU | Egypt | Dr Ahmed Sharaf
I .C. U Triangle
e-Health

## Slide 3: Step 1 - State of the art
WHAT | HOW E-HEALTH IS TAUGHT IN EUROPEAN COUNTRIES AND IN BENEFICIARY COUNTRIES
WHEN | FROM MAY 2020 TO SEPTEMBER 2020
WHO | ALL PARTNERS
HOW | COLLECTING INFORMATION ABOUT E-H-EALTH EDUCATION SYSTEM IN EGYPT, LEBANON AND EU
EXPECTED RESULTS | A PHOTOGRAPH OF E-HEALTH EDUCATION SYSTEM IN EUROPE AND BENEFICIARY COUNTRIES
I .C. U Triangle
e-Health

## Slide 4: Step 2 - Differences between Lebanese and Egyptian education systems on E-Health and EU experiences
WHAT | IDENTIFY THE DIFFERENCES BETWEEN DIVERSE EDUCATION SYSTEMS IN E-HEALTH
WHEN | JULY 2020 TO OCTOBER 2020
WHO | UNIGE, LNU, TALTECH, NDU, BEU, ASU, SU
HOW | COMPARING THE INFORMATION COLLECTED IN STEPS 1
EXPECTED RESULTS | MATRIX SHOWING SIMILARITIES AND DIFFERENCES BETWEEN THE EVALUATED SYSTEMS
I .C. U Triangle
e-Health

## Slide 5: Step 3 - Education needs
WHAT | TO IDENTIFY THE TRAINING NEEDS THAT THE COURSE MUST ANSWER TO
WHEN | JULY 2020 TO OCTOBER 2020
WHO | ALL PARTNERS
HOW | COLLECT FROM ALL PARTNERS THE POSSIBLE GAPS THAT THE COURSE SHOULD COVER
EXPECTED RESULTS | REPERTOIRE OF KNOWLEDGE AND SKILLS THAT STUDENTS MUST POSSESS AT THE END OF THE COURSES
I .C. U Triangle
e-Health

## Slide 6: Step 4 - Enhance Lebanese and Egyptian strengths and use EU strengths to improve the weaknesses of Lebanese and Egyptian education system on E-Health
WHAT | IDENTIFYING THE STRENGTHS AND WEAKNESSES OF THE E-HEALTH EDUCATION SYSTEM IN LEBANON AND EGYPT
WHEN | NOVEMBER 2020
WHO | UNIGE, LNU, TALTECH, NDU, BEU, ASU, SU
HOW | ANALYZING THE RESULTS OBTAINED IN STEP 2 AND 3
EXPECTED RESULTS | COMBINING BEST PRACTICES OF ALL COUNTRIES
I .C. U Triangle
e-Health

## Slide 7: Step 5 - Choose the architecture of the courses
WHAT | SELECT THE ARCHITECTURE OF THE COURSES
WHEN | DECEMBER 2020
WHO | UNIGE, LNU, TALTECH, NDU, BEU, ASU, SU
HOW | SELECT BETWEEN: Short [30 ECTS (3 modules) + 15 ECTS pre-diploma Internship] and long [60 ECTS (6 modules) + 15 ECTS pre-diploma Internship] Short [30 ECTS (6 modules) + 15 ECTS pre-diploma Internship] and long [60 ECTS (6 modules) + 15 ECTS pre-diploma Internship]
EXPECTED RESULTS | DEFINITION OF THE ARCHITECTURE OF THE COURSES
I .C. U Triangle
e-Health

## Slide 8: Step 6 - Decide the contents of the modules
WHAT | DEFINE THE CONTENTS AND OBJECTIVES OF THE INDIVIDUAL MODULES THAT WILL MAKE UP THE COURSES
WHEN | DECEMBER 2020 TO JANUARY 2021
WHO | UNIGE, LNU, TALTECH, NDU, BEU, ASU, SU
HOW | DESCRIBE THE OUTCOMES OF EACH MODULE AND HOW TO REACH THEM
EXPECTED RESULTS | SILLABUS OF THE COURSES
I .C. U Triangle
e-Health

## Slide 9: Step – 7 Start a pilot experience
WHAT | ACTIVATE THE MODULES TO VERIFY THEIR FEASIBILITY AND ABILITY TO PRODUCE THE EXPECTED TRAINING RESULTS
WHEN | FEBRUARY 2021 JULY 2021
WHO | NDU, BUE, ASU, SU
HOW | STARTING THE MODULES WITH VOLUNTEER STUDENTS BY RECOGNIZING THEM THE PATHS TAKEN WITHIN THEIR OWN TRAINING PROCESS
EXPECTED RESULTS | COURSE FEASIBILITY VERIFICATION
I .C. U Triangle
e-Health

## Slide 10: Step – 8 Evaluate pilot experience by means of questionnaire/focus groups submitted to students and professors
WHAT | VERIFICATION OF THE EFFECTIVENESS OF THE CHOICES MADE
WHEN | JULY 2021 TO SEPTEMBER 2021
WHO | NDU, BUE, ASU, SU
HOW | BY MEANS OF QUESSTIONNAIRE/ FOCUS GROUP TO STUDENTS AND PROFESSORS
EXPECTED RESULTS | INFORMATION ABOUT STRENGHTS AND WEAKNESS OF THE MODULES
I .C. U Triangle
e-Health

## Slide 11: Step 9 - Improve the courses and realise the final version
WHAT | IMPROVE THE COURSES AND REALIZE THE FINAL VERSION
WHEN | OCTOBER 2021 TO DECEMBER 2021
WHO | UNIGE, LNU, TalTech, NDU, BUE, ASU, SU
HOW | USING THE DATA COLLECTED IN STEP 8
EXPECTED RESULTS | FINAL VERSION OF THE COURSES
I .C. U Triangle
e-Health

## Slide 12: Step 10 - Reach accreditation in Lebanon and Egypt
WHAT | OBTAIN RECOGNITION OF THE COURSES FROM THE RESPECTIVE MINISTRIES OF EDUCATION
WHEN | JANUARY 2022
WHO | NDU, BUE, ASU, SU
HOW | PRESENTING THE NECESSARY DOCUMENTATION TO OBTAIN THE RECOGNITION IN THE APPROPRIATE LOCATIONS AND FOLLOWING THE PROCEDURE OF THE FILE
EXPECTED RESULTS | ACTIVATION OF COURSES RECOGNISED BY THE RESPECTIVE MINISTRIES OF EDUCATION FROM THE ACADEMIC YEAR 2022-2023
I .C. U Triangle
e-Health